## Mind Maps
MIND MAP
Project Name : Dazzle

## TestScenarios
Project Name | Dazzle.bd.con
Reference Document | FRS
Created By | Md.Aminul Islam
Creation Date | 18-07-2025
Approval Date | 25-07-2025
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the working of the "Register" functionality. | P0 | 25
TS_002 |  | Validate the "Login" functionality | P0 | 16
TS_003 |  | Validate the working of "Forget Password?" functionality. | P1 | 11
TS_004 |  | Validate the "Login with google" functionality | P2 | 2
TS_005 |  | Validate the "Login with phone number" functionality | P3 | 9
TS_005 |  | Validate the functionality of "Search" actions. | P4 | 12
TS_006 |  | Validate the "Cart" functionality | P1 | 8
TS_007 |  | Validate the "Check Out" functionality | P2 | 5
TS_008 |  | Validate the "Order Tracking" functionality | P2 | 9
TS_009 |  | Validate the "Pre Order" functionality | P3 | 24
TS_010 |  | Validate the "Header Section" functionality | P5 | 6
TS_011 |  | Validate the "Footer Section" functionality | P1 | 9
TS_012 |  | Validate the "Body Section" functionality | P2 | 12
TS_013 |  | Validate the "GUI" | P1 | 8

## TestCase
Product Name |  | Dazzle | TC Start Date | 18/07/2025 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 25/07/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 144
Epic |  |  | Test Case Developed By | Md. Aminul Islam | Browser (tested) | Yes |  |  |  |  | FAIL | 16
Developer Name (TL) |  |  | Test Case Reviewed By | 0 | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 160
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Dazzle' 3. Go to the website. |  |  | Passed
2 |  |  | Register | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing. | Should be clicked on the "Register" link. | Found as per expectation. | Browsers-Google Chrome, Microsoft Edge | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
3 |  |  |  | Verify the displayed element are in alignment from. | Elements should be in aligment from. | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
4 |  |  |  | Verify that the size, color, and UI of different elements should match the specifications. | Should be as per the client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
5 |  |  |  | Verify that the login page of the application is responsive and aligns properly on different screen resolutions and devices | Application should be reponsive | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
6 |  |  |  | Verify register page title. | The title should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
7 |  |  |  | Verify register page image | The image should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
8 |  |  |  | Verify by clicking on the submit button for blank input. | Click on the submit button for a blank input shuould not register | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
9 |  |  |  | Verify all fields related to registration present on the registration form. | Should be all fields related to registation present on the registration form | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
10 |  |  |  | Verify Password field should have validation for a minimum of 8 to maximum of 16 characters | Password should be validation for a minimum of 8 to 16 characters | Found not as per expectation. | 12345666666666600 | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link | Screenshort |  | Failed
11 |  |  |  | Verify must contain one special character, at least one uppercase character, and have a numerical. | Should not register password must special character, at least one uppercase and numerical number | Found not as per expectation. | 12345678 | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link | Screenshort |  | Failed
12 |  |  |  | Verify password added by the user should be protected, encrypted, and shown in an asterisk(***). | The password entered should be in protected and encrypted form. | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
13 |  |  |  | Verify whether the validation is added for the password and confirm whether passwords are the same or not. | Password and confirm password should be same | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
14 |  |  |  | Verify an eye icon added to the password and confirm the password field. | Should be there a eye icon | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
15 |  |  |  | Verify by clicking on the eye icon password should be shown for both passwords and confirm password fields. | Password showing should be eye icon clicking | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
16 |  |  |  | Verify that validation is added to the email field, only valid emails should be allowed to register successfully. | Valid emails should be allowed to registration | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
17 |  |  |  | Verify the error message should display after just entering an email address and leaving the password field blank. | Should give an error message | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
18 |  |  |  | Verify the error message should display after just entering a password and leaving the email, name and phone number field blank. | The error message should display after just entering a password | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
19 |  |  |  | Verify that the user adds blank spaces and clicks on the register button an error message should be shown. | The error message should display after blank spaces | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
20 |  |  |  | Verify users can register successfully by entering valid credentials. | Register successfully should be entering valid credentials | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
21 |  |  |  | Verify the displayed error message grammar should be correct. | Erro massage should be grammaticaly correct | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
22 |  |  |  | Verify the displayed error message spell should be correct. | The spelling of error message should be correct. | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
23 |  |  |  | Test by trying to register with an already registered email address. | Should not register by already used email | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
24 |  |  |  | Verify all spelling mistakes on the Register page. | Should not spelling mistakes on register page | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link |  |  | Passed
25 |  |  |  | Verify the error message should display after just entering full name as a number | Error massage should not be showing | Found not as per expectation. | 123456 | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link | Screenshort |  | Failed
26 |  |  |  | Verify the error message should display after just entering full name as a sepecial characters | Error massage should not be showing | Found not as per expectation. | ###%$ | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link | Screenshort |  | Failed
26 |  |  |  | Checking by inputing invalid name format | Should not be accept inputing invalid name format | Found not as per expectation. | Md.Aminul Islam #$#$#12 | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link | Screenshort |  | Failed
27 |  |  | Login | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing | Should be click on the "Login" link | Found as per expectation. | Browsers-Google Chrome, Microsoft Edge | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
28 |  |  |  | Verify the displayed element are in alignment from | Elements should be in alignment from | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
29 |  |  |  | Verify that the size, color, and UI of different elements should match | Should be as per the client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
30 |  |  |  | Verify register page title. | The title should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
31 |  |  |  | Verify register page image | The title image should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
32 |  |  |  | Verify that the login page of the application is responsive and aligns | Element should be responsive and aligns | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
33 |  |  |  | Verify the cursour in the "Email or Phone box " by default. | Fields sould be in empty position | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
34 |  |  |  | Verify that the user will be able to log in with their account with the correct credential | User should be able to login with correct credintial | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
35 |  |  |  | Verify the login screen will appear after clicking on a login link or login button. | Should be clicking login button will login screen | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
36 |  |  |  | Verify that the password entered should be in encrypted form. | The password entered should be in encrypted form. | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
37 |  |  |  | Verify whether an eye icon is added to the password field or not | Should be there a eye icon | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
38 |  |  |  | Verify the error message should display after just entering a password and leaving the email field blank. | Should give and error massage | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
39 |  |  |  | Verify the error message should display after just entering an email address and leaving the password field blank. | Should give and error massage | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
40 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation. | tashfiq.dipto124238@@gmail.com | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
41 |  |  |  | Checking by inputing valid email format | Should accept the provided input a. | Found as per expectation. | tashfiq.dipto124238@@gmail.com | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
42 |  |  |  | Checking by inputting invalid mobile number . | Should not accept the provided input and display an error message | Found as per expectation. | 19348389921 | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. |  |  | Passed
43 |  |  | Forget Password | Verify that forget password link should be present on the login screen. | Should be present | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
44 |  |  |  | Verify that on clicking on the forget password link forget password page should open. | Click on the link page should be open | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
45 |  |  |  | Verify that the email field is present on the forget password page to recover the password. | Should be present email field | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
46 |  |  |  | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing | Should be click on the "Forgot your password" link | Found as per expectation. | Browsers-Google Chrome, Microsoft Edge | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
47 |  |  |  | Verify the displayed element are in alignment from | Elements should be in alignment from | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
48 |  |  |  | Verify that the size, color, and UI of different elements should match | Should be as per the client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
49 |  |  |  | Verify that the forgot your password page of the application is responsive and aligns | Should be as per the client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
50 |  |  |  | Verify login page title. | The title should be as client requirment | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
51 |  |  |  | Verify register page image | The title image should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
52 |  |  |  | Verify Submit button should be present on the page. | Should be present | Found as per expectation. | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link |  |  | Passed
53 |  |  |  | Verify Submit button should be working or not. | Should be working | Found not as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'forget password' link | Screenshort |  | Failed
54 |  |  | Login with google | Verify that on clicking on the Login with google button sign with google page should open. | Click on the link page should be open | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with Google' button |  |  | Passed
55 |  |  |  | Verify signin page properly working | Should be proper working | Found not as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with Google' button | Screenshort |  | Failed
56 |  |  | Search Functionality | Verify the search field is present and aligned | Should be as per client requirement | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
57 |  |  |  | verify whether placeholder text is added on search or not | Elements should be in placeholder in search bar | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
58 |  |  |  | Verify spelling and grammar should be correct for placeholder text. | Placeholder should be grammaticaly correct | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
59 |  |  |  | Verify search is functional and generating the correct result for correct keywords or not by adding a valid search. | Should be showing the currect result | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
60 |  |  |  | Verify the search is working by adding keywords and on click on the search button. | Should be showing the currect result | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
61 |  |  |  | Verify if the user can paste the keyword with the mouse. | Should be past the keyword with the mouse | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
62 |  |  |  | Verify an error message displayed by entering invalid keywords in the search field and clicking the search button. | Error Message should be showing | Found not as per expectation | phone i 16pro Max | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section | Screenshort |  | Failed
63 |  |  |  | Verify an error message should display for blank input. | Error Message should be showing | Found not as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section | Screenshort |  | Failed
64 |  |  |  | Verify and observe how much time is required for getting the search result. | Search result should be time is required | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
65 |  |  |  | Verify the search result generated by the search in the correct order as per requirement. | The title should be as client requirment | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
66 |  |  |  | Verify whether suggestions are shown or not on adding a keyword to the search. | Suggestions should be showing | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section |  |  | Passed
67 |  |  |  | Verify the max and min range for the search keyword. | Should be range in search keayword | Found not as per expectation | iphone iphone iphone….... | 1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section | Screenshort |  | Failed
68 |  |  | Cart Button | confirm whether the Add to Cart button is present or not on the webpage for the product | Should be present cart button from webpage for the product | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
69 |  |  |  | Make sure user-selected products should be added to the cart page. | Should be added the product on the cart page | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
70 |  |  |  | Test users can add more than one item on the cart page. | Should be added more than one item | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
71 |  |  |  | Verify the price of the selected product is clearly shown or not on the cart page. | Should be showing price of selected product on the cart page | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
72 |  |  |  | Verify whether the product delivery charges are mentioned on the cart page or not. | Delivery charge should be not showing in cart page | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
73 |  |  |  | Verify whether the user can add multiple products to the cart or not. | Should be multiple product add to cart | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
74 |  |  |  | Verify whether the user can add the same product multiple times or not. | Should be one time in same product add to cart | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
75 |  |  |  | Verify the total price of all products is shown on the page or not. | Should be all product price shown on the page | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner |  |  | Passed
76 |  |  | Header Section | Verify the header section added on the website. | Should be added | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
77 |  |  |  | Verify header section is aligned. | Elements should be in alignment from | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
78 |  |  |  | Verify whether link text should be readable or not. | Should be link text readable | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
79 |  |  |  | Verify whether all links should be opening on the header or not. | Link should be opened | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
80 |  |  |  | Verify on click on the link on the header the correct page should be open | Should be open in correct page | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
81 |  |  |  | Verify on the mouse hover color change or not for the link added on the header menu | Should not be mouse hove color change in menu | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" |  |  | Passed
82 |  |  | Order Tracking | Verify the alignment of displayed elements on the order track should be compatible in cross browsers testing | Should be click on the "order track" link | Found as per expectation | Browsers-Google Chrome, Microsoft Edge | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
83 |  |  |  | Verify that the size, color, and UI of different elements should match | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
84 |  |  |  | Verify the search field is present and aligned | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
85 |  |  |  | verify whether placeholder text is added on search or not | Elements should be in placeholder in search bar | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
86 |  |  |  | Verify spelling and grammar should be correct for placeholder text. | Placeholder should be grammaticaly correct | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
87 |  |  |  | Verify search button is present on the field. | Should be there a search button | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
88 |  |  |  | Verify cursor should be present on click on the search button | Should be a clickable | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
89 |  |  |  | Verify on the mouse hover color change or not for the link added on the header menu | Should be mouse hove color change in menu | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
90 |  |  |  | Verify search is functional and generating the correct result for correct keywords or not by adding a valid search. | Should be showing the currect result | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
91 |  |  |  | Verify an error message displayed by entering invalid keywords in the search | Error massage should be showing | Found not as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. | Scrrenshort |  | Failed
92 |  |  |  | Verify an error message should display for blank input. | Error massage should be showing | Found not as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. | Screenshort |  | Failed
93 |  |  | Pre Order | Verify the alignment of displayed elements on the pre-order screen should be compatible in cross browsers testing. | Should be clicked on the "Pre-order" link. | Found as per expectation | Browsers-Google Chrome, Microsoft Edge | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
94 |  |  |  | Verify the displayed element are in alignment from. | Elements should be in aligment from. | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
95 |  |  |  | Verify that the size, color, and UI of different elements should match | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
96 |  |  |  | Verify that the pre order page of the application is responsive and aligns | Element should be responsive and aligns | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
97 |  |  |  | Verify pre order page title. | The title should be as client requirment | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
98 |  |  |  | verify whether placeholder text is added on search or not | Elements should be in placeholder in search bar | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
99 |  |  |  | Verify spelling and grammar should be correct for placeholder text. | Placeholder should be grammaticaly correct | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
100 |  |  |  | Verify enter product name or url fild present or not | Should be present product name or url fild | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
101 |  |  |  | Verify by clicking in the input URL field that the user can access the field. | Should be access the field | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
102 |  |  |  | Verify users can type URLs in the field. | user can type should be Url | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
103 |  |  |  | Check by adding a valid URL with https:// | Should be URL with https:// | Found not as per expection | dazzle.com.bd/product/macbook-air-m1-13-inch | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. | Screenshort |  | Failed
104 |  |  |  | Check by adding spaces between the URL. | Should not adding space between the URL | Found not as per expection | dazzle.co m.bd/prod uct/macbook-air-m1-13-inch | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. | Screenshort |  | Failed
105 |  |  |  | Verify upload file button or link is present. | Should be present upload file button or link | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
106 |  |  |  | Verify the upload button or link should be clickable. | Should be Clickable | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
107 |  |  |  | Verify icon added with the upload button is in the design and is aligned or not. | Elements should be in aligment from. | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
108 |  |  |  | Verify that the user can only be able to upload the allowed files only. For example doc, Docx or pdf, or image files like jpg, png, etc. | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
109 |  |  |  | Verify on uploading file loader should be shown. | Should be showing | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
110 |  |  |  | Inputting name with special characters, number and decimal number . | Should not accept this special character as provided input. | Found as per expectation | Md. Aminul Islam #$#12., | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. | Screenshort |  | Failed
111 |  |  |  | Checking by inputting valid mobile number. | Should accept the provided input valid mobile number | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
112 |  |  |  | Checking by inputting invalid mobile number. | Should not accept the provided input and display an error message | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
113 |  |  |  | Checking by inputing valid email format | Should accept the provided input. | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
114 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
115 |  |  |  | Check by inputing invalid address format | Should not accept the provided input and display an error message | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
116 |  |  |  | Verify submit button properly work or not | Should be button properly work | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner. |  |  | Passed
117 |  |  | Body Section | Verify products or items shown on the webpage clearly. | Should be Clearly | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
118 |  |  |  | Make sure that the items are categorized or not by the category name. | Iteam and category name should be should be clearly | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
119 |  |  |  | Verify that the image added to the product should not be broken or blurred. | Image should be clear. | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
120 |  |  |  | Verify product size, dimensions and quality are mentioned under the product or not. | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
121 |  |  |  | Verify whether product reviews by the customer are added or not. | Customer should be reviews | Found not as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section | Screenshort |  | Failed
122 |  |  |  | Confirm whether the images for the products are available or not. | Image should be available | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
123 |  |  |  | Confirm the user-selected product detail page opens as the user clicks on the image or name of the product. | Should be as per the client requirement | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
124 |  |  |  | Confirm whether the available color of the item should be shown on the webpage or not. | Product color should be showing webpage | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
125 |  |  |  | Check the correct price of the product should be displayed on the webpage. | Product price should be displayed | Found as per expectation | None | 1. Go to URL "https://motionview.com.bd/" 2. Go to body section |  |  | Passed
126 |  |  | Footer Section | Verify the footer section is aligned at the end of the page. | Should be aligned in footer section | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
127 |  |  |  | Verify element is aligned at the footer section or not. | Element should be aligned | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
128 |  |  |  | Verify footer section should be the same for all pages. | Should be the same all pages | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
129 |  |  |  | Verify the logo shown at the footer. | Logo should be present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
130 |  |  |  | Verify logo is aligned on the footer. | Logo should be present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
131 |  |  |  | Verify all social links with icons added on the footer. | Should be present social media icon | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
132 |  |  |  | Verify no spelling mistakes for the text on the footer section. | No spelling should be footer section | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
133 |  |  |  | Verify there must be equal space for the elements links, button, and social links from top and bottom at the footer section links from top and bottom at the footer section. | element should be equal space | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
134 |  |  |  | Verify no broken link is found on the footer. | No broken link should be found | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
135 |  |  |  | Verify whether the copyright section is added to the footer or not. | Copyright section should be present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
136 |  |  |  | Verify correct year was added to the footer section or not. | Correct year should be present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
137 |  |  |  | Verify whether the copyright icon is added or not on the footer section. | Should be present copyright icon | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd/" 2. Scroling the down |  |  | Passed
138 |  |  | Login With Phone Number | Verify the alignment of displayed elements on the login with phone number screen should be compatible in cross browsers testing | Should be click on the "Login with phone number" link | Found as per expectation | Browsers-Google Chrome, Microsoft Edge | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
139 |  |  |  | Verify the displayed element are in alignment from | Element should be alignment from | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
140 |  |  |  | Verify that the size, color, and UI of different elements should match | Should be as per the client requirement | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
141 |  |  |  | Verify that the login with phone number page of the application is responsive and aligns | Element should be responsive and aligns | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
142 |  |  |  | Verify for verification whether valid and correct OTP is generated or not. | Correct OTP should be generated | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
143 |  |  |  | Verify OTP code should be valid only for one time or not. | Valid should be only for one time | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
144 |  |  |  | Verify OTP code is sent to the user successfully or not within time or not. | Should be OTP code is sent to the user successfully | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
145 |  |  |  | Verify OTP code is only numeric or alphanumeric | Should be only numeric | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
146 |  |  |  | Verify Login button properly work | Should be properly work | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with phone number' button |  |  | Passed
147 |  |  | GUI | Verify that all the elements (checkboxes, radio button, text fields etc) on the webpage are aligned or not. | All element should be aligned | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
148 |  |  |  | Make sure that icons on the webpage align with the web page. | Icon Should be align | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
149 |  |  |  | Verify that placeholder text on the input field is present and visible or not. | Should be placeholder text on the input field | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
150 |  |  |  | Verify whether the font size for the content on the webpage is readable or not. | Should be readable | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
151 |  |  |  | Confirm the font colour for the content on the web page or not. | Font colour for the content should be webpage | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
152 |  |  |  | Verify the text on the images should be readable. | Images should be readable | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
153 |  |  |  | Verify the spellings should be correct on the web page. | Spelling should be correct | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
154 |  |  |  | Verify the correct page should be open on click on the link. | Correct page opent link should be click | Found as per expectation | None | 1. Goto the URL https://www.dazzle.com.bd/ |  |  | Passed
155 |  |  | Check Out | Verify whether the checkout or payment button on the cart webpage is present or not. | Should be present checkout webpage is present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner 3. Go to bottom section click on "Check Out" button |  |  | Passed
156 |  |  |  | Make sure on the payment page that different payment methods are available or not for the user. | Should be available different payment methods | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner 3. Go to bottom section click on "Check Out" button |  |  | Passed
157 |  |  |  | Test payment is done successfully by adding valid credit/debit card credentials. | Should be valid credentials | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner 3. Go to bottom section click on "Check Out" button |  |  | Passed
158 |  |  |  | Verify delivery address form are present | Should be present | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner 3. Go to bottom section click on "Check Out" button |  |  | Passed
159 |  |  |  | Verfy save button are properly working. | Should be working | Found as per expectation | None | 1. Go to URL "https://dazzle.com.bd" 2. Click on the cart icon in the right corner 3. Go to bottom section click on "Check Out" button |  |  | Passed

## Test Summary Report
Test Case Report
Project Name | Dazzle BD LTD |  |  |  |  | Result |  | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Module Name | [5 empty] | Total No. | Status
Feature Name
Test Case Version | 1 |  |  |  |  | 144 | PASS
Written By | Md.Aminul Islam |  |  |  |  | 16 | FAIL
Executed By | Md.Aminul Islam |  |  |  |  | 0 | Not Executed
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 144 | 16 | 0 | 0 | 160
Grand Total | 144 | 16 | 0 | 0 | 160
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Report
#SL-01
Issue: Password validation minimum 8 characters and maximum 16 characters.
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link
Enviroment: Production
Module:Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Password should be minimum 8 character and maximum 16 character.
Expected: Password should be validation for a minimum of 8 to 16 characters
Responsible QA:
Bug Report
#SL-02
Issue: Register password not must special character, at least one uppercase and numerical number
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link
Enviroment: Production
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Register password not must special character, at least one uppercase and numerical number
Expected: Register password must special character, at least one uppercase and numerical number
Responsible QA:
Bug Report
#SL-03
Issue: Error Massage not showing.
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link
Enviroment: Production
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Error massage not showing
Expected: Error massage must be showing
Responsible QA:
Bug Report
#SL-04
Issue: Invalid name formating.
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click the "Register" link
Enviroment: Production
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Invalid name formating
Expected: Should not accepted this invalid name format.
Responsible QA:
Bug Report
#SL-05
Issue: Forget Password button not working.
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with Google' button
Enviroment: Production
Module: Forget Password.
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshor: Forget password button not working.
Expected: Forget Password button should be working
Responsible QA:
Bug Report
#SL-06
Issue: Login with google page not working
1. Goto the URL https://www.dazzle.com.bd/ 2. Click on the Login button in the right corner. 3. Click 'Login with Google' button
Enviroment: Production
Module: Login with google
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Login with google page not working.
Expected: Login with google page poperly working
Responsible QA:
Bug Report
#SL-07
Issue: Error massage not showing
1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section
Enviroment: Production
Module: Search functionality
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Error massage not showing.
Expected: Enter invalid keyword error massage must show on.
Responsible QA:
Bug Report
#SL-08
Issue: Error massage not showing
1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section
Enviroment: Production
Module: Search functionality
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Error massage not showing.
Expected: Blank input error massage must show on.
Responsible QA:
Bug Report
#SL-09
Issue: No range in Search keyword
1. Go to URL "https://dazzle.com.bd/" 2. Click on the search button in header section
Enviroment: Production
Module: Search functionality
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: No range in search keyword.
Expected: Should be range in search keayword.
Responsible QA:
Bug Report
#SL-10
Issue: Order invalid keyword error massage not showing.
1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner.
Enviroment: Production
Module: Order Tracking
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Error massage not showing.
Expected: Error massage should be showing
Responsible QA:
Bug Report
#SL-11
Issue: Blank input field error massage not showing.
1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner.
Enviroment: Production
Module: Order Tracking
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Error massage not showing.
Expected: Error massage should be showing
Responsible QA:
Bug Report
#SL-12
Issue: Should not be URL with https://
1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner.
Enviroment: Production
Module: Pre order
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Should not be URL with https://
Expected: Should be URL with https://
Responsible QA:
Bug Report
#SL-13
Issue: Adding space between the URL
1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner.
Enviroment: Production
Module: Pre order
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Adding space between the URL
Expected: Should not adding space between the URL
Responsible QA:
Bug Report
#SL-14
Issue: Inputting name with special characters, number and decimal number .
1. Go to URL "https://motionview.com.bd/" 2. Click on Right Corner.
Enviroment: Production
Module: Pre order
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort
Expected: Should not accept this special character as provided input.
Responsible QA:
Bug Report
#SL-15
Issue: Product reviews by the customer are not added.
1. Go to URL "https://motionview.com.bd/" 2. Go to body section
Enviroment: Production
Module: Body Section
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshort: Product reviews by the customer are not added.
Expected: Customer should be reviews.
Responsible QA:

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (138/138)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/138)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (122/138)*100 = 88%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (16/138)*100 = 12%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A